## Cover
PARTNER FIRM IMPLEMENTATION PLAN — ONBOARDING ROADMAP
PARTNER FIRM: | [Partner Firm Name]
PRIMARY CONTACT: | [Name, Title]
FIDUCIENT ADVISOR: | Joe Cortese
PLAN DATE: | April 02, 2026
PARTNERSHIP OVERVIEW — THREE PILLARS OF SERVICE
ASSET ALLOCATION |  |  | MANAGER SELECTION |  |  | MARKETING & CASE SUPPORT
Frontier Engineer® proprietary process ¦ Capital market assumptions modeling ¦ Bespoke model portfolios tailored to your clients ¦ Tactical allocation guidance ¦ Sub-asset class research |  |  | 6-stage institutional due diligence ¦ Fixed income, equity, real assets & alternatives ¦ Private equity & hedge fund access ¦ ESG/SRI/Mission-aligned options ¦ Approved manager list delivery |  |  | 100+ annual content pieces ¦ White-labeled market commentary ¦ Quarterly investment reviews ¦ Pitch deck & case support ¦ Portal access & training
IMPLEMENTATION PHASES AT A GLANCE
PHASE | DESCRIPTION | TIMELINE | OWNERSHIP | PRIORITY | # TASKS | % COMPLETE | STATUS
Phase 1 | Kickoff & Discovery | Week 1 | Joint | High | 5 | 0% | Not Started
Phase 2 | Manager Selection & Due Diligence | Weeks 1–4 | Fiducient | High | 9 | 0% | Not Started
Phase 3 | Asset Allocation & Portfolio Const. | Weeks 2–4 | Fiducient | High | 5 | 0% | Not Started
Phase 4 | Marketing & Communications | Weeks 2–6 | Joint | High | 4 | 0% | Not Started
Phase 5 | Reporting & Technology | Weeks 3–6 | Fiducient | Medium | 4 | 0% | Not Started
Phase 6 | Business Development & Case Support | Ongoing | Joint | Medium | 3 | 0% | Not Started
Phase 7 | Specialized Services | As Needed | Fiducient | Low | 4 | 0% | Not Started
Phase 8 | Rollout & Ongoing Partnership | Ongoing | Joint | High | 4 | 0% | Not Started
CONFIDENTIAL — For the exclusive use of Fiducient Advisors clients and prospective clients. Past performance does not indicate future performance and there is risk of loss.
| FINANCIAL INSTITUTIONS PARTNERSHIP

## Implementation Plan
FIDUCIENT ADVISORS ¦ PARTNER FIRM IMPLEMENTATION PLAN
Financial Institutions Onboarding — Detailed Task Tracker
PHASE / TASK | DESCRIPTION | CLIENT OWNERSHIP | FIDUCIENT OWNERSHIP | TIMELINE | PRIORITY | STATUS | DELIVERABLES | NOTES / UPDATES
PHASE 1: KICKOFF & DISCOVERY
Initial Partnership Meeting | Introduce dedicated service team, review partnership structure, establish communication cadence & key contacts | ✓ | ✓ | Day 1 | High | Not Started | Meeting agenda, contact list
Firm Assessment & Needs Analysis | Comprehensive review of current investment platform, client segments, AUM breakdown, and growth objectives | ✓ |  | Week 1 | High | Not Started | Needs assessment questionnaire
Existing Manager Inventory | Document all current/legacy managers for evaluation against Fiducient recommended list | ✓ |  | Week 1 | High | Not Started | Manager inventory spreadsheet
Technology & Systems Review | Assess current technology stack, reporting systems (Morningstar, Orion, etc.) and integration requirements | ✓ | ✓ | Week 1 | Medium | Not Started | Systems checklist
Compliance & Regulatory Review | Introduction to CCO, review compliance requirements, establish documentation protocols and fiduciary framework |  | ✓ | Week 1 | High | Not Started | Compliance framework document
PHASE 2: MANAGER SELECTION & DUE DILIGENCE
Introduction to Research Team | Meet investment research professionals; overview of 6-stage institutional due diligence process |  | ✓ | Week 1 | High | Not Started | Research team bios, process overview
Performance Reporting Setup | Configure existing managers within Fiducient systems for ongoing performance reporting and peer group rankings |  | ✓ | Immediate | High | Not Started | Performance dashboard access
Legacy Manager Evaluation | In-depth review of existing manager stable — retain, terminate, or add recommendations | ✓ | ✓ | Weeks 1–2 | High | Not Started | Manager evaluation report
Manager DD — Fixed Income | Comprehensive analysis: investment grade, TIPS, high yield, EM bonds, municipals |  | ✓ | Weeks 2–3 | High | Not Started | Fixed income manager report
Manager DD — Equities | Analysis across all caps, domestic, international, emerging markets |  | ✓ | Weeks 2–3 | High | Not Started | Equity manager report
Manager DD — Real Assets | Review of real estate, infrastructure, commodities, natural resources, timberland options |  | ✓ | Weeks 3–4 | Medium | Not Started | Real assets manager report
Manager DD — Alternatives | Hedge funds, private equity, marketable alternatives evaluation (if applicable to client base) |  | ✓ | Weeks 3–4 | Medium | Not Started | Alternatives manager report
ESG / SRI / Mission-Aligned Options | Review of mission-aligned investing capabilities and manager options for applicable client segments |  | ✓ | As Needed | Low | Not Started | MAI framework document
Approved List Delivery | Comprehensive investment search analysis with preferred managers for each asset class |  | ✓ | Weeks 3–4 | High | Not Started | Final approved manager list
PHASE 3: ASSET ALLOCATION & PORTFOLIO CONSTRUCTION
Frontier Engineer® Methodology Review | Deep dive into proprietary asset allocation tool; review of capital market assumptions and MPT framework |  | ✓ | Weeks 1–2 | High | Not Started | Frontier Engineer demo / training
Client Segmentation Analysis | Identify client segments and appropriate model portfolio tiers (conservative, moderate, growth, etc.) | ✓ | ✓ | Weeks 2–3 | High | Not Started | Segmentation framework
Model Portfolio Development | Creation of Frontier Engineer® bespoke model portfolios tailored to your specific client segments |  | ✓ | Weeks 2–4 | High | Not Started | Model portfolio specifications
Transition Strategy Discussion | Plan for transitioning existing portfolios to new models including tax considerations and timing | ✓ | ✓ | Weeks 2–4 | High | Not Started | Transition roadmap document
Tactical Allocation Guidance | Review of integrated strategic/tactical approach and annual adjustment process |  | ✓ | Ongoing | Medium | Not Started | Tactical guidance framework
PHASE 4: MARKETING & COMMUNICATIONS
Content Library Introduction | Overview of 100+ annual marketing pieces available for white-labeling and distribution |  | ✓ | Weeks 2–4 | High | Not Started | Content library access / catalog
White-Label Material Selection | Select initial pieces to private label: Monthly Review, Quarterly Commentary, Financial Planning Guide, etc. | ✓ | ✓ | Weeks 2–4 | High | Not Started | Selected materials list
Portal Demo & Training | Demonstration of client-facing portal, document access, video/newsletter tools and reporting dashboards |  | ✓ | Weeks 3–4 | Medium | Not Started | Portal credentials / training guide
Marketing Calendar & Cadence | Establish schedule for market commentary delivery, distribution cadence, and email marketing setup | ✓ | ✓ | Weeks 4–6 | Medium | Not Started | Marketing calendar template
PHASE 5: REPORTING & TECHNOLOGY
Benchmarking Configuration | Establish appropriate benchmarks and custom blended benchmarks aligned to model portfolios | ✓ | ✓ | Weeks 2–4 | High | Not Started | Benchmark documentation
Manager Attribution Reports | Set up manager attribution analysis and fact sheet generation workflow |  | ✓ | Weeks 3–4 | Medium | Not Started | Attribution report samples
Portfolio Engineer® Rebalancing Setup | Training on rebalancing system, trigger point methodology and drift monitoring |  | ✓ | Weeks 4–6 | Medium | Not Started | Rebalancing protocol
FLASH Memo Protocol | Establish process for timely manager change/watch list communications |  | ✓ | Weeks 2–4 | High | Not Started | FLASH memo templates
PHASE 6: BUSINESS DEVELOPMENT & CASE SUPPORT
Sales Strategy Discussion | Review business development strategies, referral activity, growth initiatives, and RFP process | ✓ | ✓ | As Needed | Medium | Not Started | Growth strategy document
Subject Matter Expert Access | Establish protocol for accessing internal experts: 401(k), non-profit, family office, financial planning |  | ✓ | Weeks 4–6 | Medium | Not Started | SME contact directory
Case Support Framework | Define process for shared/referred relationships, complex client proposals, and pitch support | ✓ | ✓ | As Needed | Medium | Not Started | Case support workflow
PHASE 7: SPECIALIZED SERVICES (AS APPLICABLE)
Private Markets & UHNW Access | Review of buyout, venture capital, secondary funds, private credit, and hedge fund options for UHNW clients |  | ✓ | As Needed | Medium | Not Started | Private markets guide
401(k) / Retirement Plan Support | Capabilities for retirement plan consulting and plan sponsor fiduciary support |  | ✓ | As Needed | Low | Not Started | Retirement plan overview
Non-Profit / Foundation Services | Specialized services for nonprofit, endowment, and foundation clients including IPS and governance |  | ✓ | As Needed | Low | Not Started | Non-profit services guide
UMA / Overlay Management | Review of UMA, overlay management, and tax-managed legacy portfolio capabilities | ✓ | ✓ | As Needed | Low | Not Started | UMA service overview
PHASE 8: ROLLOUT & ONGOING PARTNERSHIP
Fiducient Onsite / Virtual Rollout | Fiducient team presents enhanced platform: investment marketing, managers, and asset allocation enhancements | ✓ | ✓ | As Needed | Low | Not Started | Rollout presentation
Quarterly Committee Meetings | Establish cadence for quarterly meetings with market commentary, manager updates, and performance review | ✓ | ✓ | Ongoing | High | Not Started | Meeting schedule / agenda template
Annual Practice Management Review | Discussions with firm leadership on firm strategy, culture, growth initiatives, and challenges | ✓ | ✓ | Annual | Medium | Not Started | Annual review agenda
Fiduciary Institute Training | Ongoing fiduciary education, governance training, and compliance support for advisor staff |  | ✓ | Ongoing | Medium | Not Started | Training curriculum
CONFIDENTIAL — For the exclusive use of Fiducient Advisors clients and prospective clients. ¦ ✓ = Primary Responsibility ¦ Generated: April 02, 2026

## Progress Dashboard
FIDUCIENT ADVISORS ¦ IMPLEMENTATION PROGRESS DASHBOARD
Real-time tracking of onboarding status across all phases
PHASE | TOTAL TASKS | NOT STARTED | IN- PROGRESS | IN- REVIEW | COMPLETE | ON HOLD | % COMPLETE
Phase 1: Kickoff & Discovery | 5 | 5 | 0 | 0 | 0 | 0 | 0%
Phase 2: Manager Selection & Due Diligence | 9 | 9 | 0 | 0 | 0 | 0 | 0%
Phase 3: Asset Allocation & Portfolio Const. | 5 | 5 | 0 | 0 | 0 | 0 | 0%
Phase 4: Marketing & Communications | 4 | 4 | 0 | 0 | 0 | 0 | 0%
Phase 5: Reporting & Technology | 4 | 4 | 0 | 0 | 0 | 0 | 0%
Phase 6: Business Development & Case Support | 3 | 3 | 0 | 0 | 0 | 0 | 0%
Phase 7: Specialized Services | 4 | 4 | 0 | 0 | 0 | 0 | 0%
Phase 8: Rollout & Ongoing Partnership | 4 | 4 | 0 | 0 | 0 | 0 | 0%
OVERALL TOTALS | 38 | 38 | 0 | 0 | 0 | 0 | 0%
STATUS LEGEND
Not Started | In-Progress | In-Review | Complete | On Hold
CONFIDENTIAL — For the exclusive use of Fiducient Advisors clients and prospective clients. ¦ Generated: April 02, 2026

## Service Scope Matrix
FIDUCIENT ADVISORS ¦ SERVICE SCOPE & CAPABILITY MATRIX
Overview of services included in your partnership — customize scope column based on engagement
SERVICE / CAPABILITY | FIDUCIENT PROVIDES | PARTNER OWNED | SCOPE FOR THIS ENGAGEMENT | TIMELINE | NOTES
MANAGER SELECTION
Introduction to Research Team & Due Diligence Process | ✓ |  | Included | Week 1 | 6-stage institutional process
Manager DD — Fixed Income | ✓ |  | Included | Weeks 2–3 | Investment grade, HY, TIPS, EM, Munis
Manager DD — Equities | ✓ |  | Included | Weeks 2–3 | All caps, domestic & intl
Manager DD — Real Assets | ✓ |  | Included | Weeks 3–4 | RE, infrastructure, commodities
Manager DD — Hedge Funds | ✓ |  | Optional | As Needed
Manager DD — Private Markets | ✓ |  | Optional | As Needed | PE, VC, private credit
Manager DD — ESG / SRI / Mission-Aligned | ✓ |  | Optional | As Needed
Active vs. Passive Decision Framework | ✓ |  | Included | Weeks 2–3
Approved Manager List Delivery | ✓ |  | Included | Weeks 3–4
ASSET ALLOCATION
Frontier Engineer® Proprietary Tool | ✓ |  | Included | Weeks 1–2 | Proprietary optimization
Capital Market Assumptions Modeling | ✓ |  | Included | Weeks 1–2 | Long-term SAA framework
Custom Model Portfolio Development | ✓ |  | Included | Weeks 2–4 | Bespoke to client segments
Tactical Allocation Guidance | ✓ |  | Included | Ongoing | Annual review cycle
Sub-Asset Class Deep Dives | ✓ |  | Included | Weeks 2–4 | FI, equity, real assets, alts
CLIENT RELATIONSHIP & REPORTING
Performance Measurement (Fund Level) | ✓ |  | Included | Immediate
Performance Measurement (Modeled Portfolio) | ✓ |  | Included | Weeks 2–4
Manager Attribution & Fact Sheets | ✓ |  | Included | Weeks 3–4
Benchmarking & Custom Blended Benchmarks | ✓ |  | Included | Weeks 2–4
FLASH Memo — Manager Change Communications | ✓ |  | Included | Weeks 2–4
Portfolio Engineer® Rebalancing System | ✓ |  | Included | Weeks 4–6
MARKETING & CONTENT
Economic & Market Commentary (100+ pieces/yr) | ✓ |  | Included | Weeks 2–4 | White-label ready
Monthly Review / Quarterly Commentary | ✓ |  | Included | Weeks 2–4 | Private labeled
Whitepapers, Videos, Podcasts, Newsletters | ✓ |  | Included | Ongoing
Marketing Calendar & Distribution Strategy | ✓ | ✓ | Included | Weeks 4–6 | Collaborative
Client Meeting Presentation Materials | ✓ |  | Included | Ongoing
Pitch Deck & Case Support | ✓ |  | Included | As Needed
BUSINESS DEVELOPMENT & SPECIALIZED
Sales Strategy & RFP Support | ✓ | ✓ | Included | As Needed
401(k) / Retirement Plan Consulting | ✓ |  | Optional | As Needed
Non-Profit / Foundation Services | ✓ |  | Optional | As Needed
UHNW / Family Office Capabilities | ✓ |  | Optional | As Needed | HF, PE, overlay mgmt
Fiduciary Institute Training & Governance | ✓ |  | Included | Ongoing
Annual Practice Management Review | ✓ | ✓ | Included | Annual | Leadership sessions
CONFIDENTIAL ¦ Scope column should be customized per engagement prior to client delivery. ¦ Generated: April 02, 2026

## Key Contacts
FIDUCIENT ADVISORS ¦ KEY CONTACTS & COMMUNICATION DIRECTORY
Dedicated team members for your partnership
FIDUCIENT ADVISORS TEAM
NAME | TITLE / ROLE | EMAIL | PHONE | RESPONSIBILITY | AVAILABILITY
Joe Cortese | Partner | jcortese@fiducient.com | (312) 224-4106 | Lead Relationship | Primary
Andrew Furney | Consultant | afurney@fiducient.com | (312) 224-4144 | Day-to-Day Advisory | Primary
Andrew Furney | Consultant | afurney@fiducient.com | (312) 224-4144 | Manager Selection & DD | As Needed
Ben Van Zoest | Consulting Analyst | bvan zoest@fiducient.com | (312) 261-5145 ext. 15145 | Content & Communications | As Needed
Ben Van Zoest | Consulting Analyst | bvan zoest@fiducient.com | (312) 261-5145 ext. 15145 | Compliance & Regulatory | As Needed
Ben Van Zoest | Consulting Analyst | bvan zoest@fiducient.com | (312) 261-5145 ext. 15145 | Reporting & Analytics | As Needed
PARTNER FIRM TEAM
NAME | TITLE / ROLE | EMAIL | PHONE | RESPONSIBILITY | AVAILABILITY
[Primary Contact] | [Title] | [email] | [phone] | Lead Contact | Primary
[Operations Contact] | [Title] | [email] | [phone] | Operations / Technology | Primary
[Compliance Contact] | [Title] | [email] | [phone] | Compliance | As Needed
[Marketing Contact] | [Title] | [email] | [phone] | Marketing & Distribution | As Needed
CONFIDENTIAL — Please complete partner firm contacts prior to client delivery. ¦ Generated: April 02, 2026